## Info
1 | Add milage to vehicle service
2 | Add anufacturer to item table
3 | Add new table for manufacture

## To do
1 | Service form ui
2 | Invoice report jasper

## task
Task name | Type | Owner | Time | Status | Reviewed by | Dead line | Current date
Documentation | Requirement | Philip | 2 days | new | Charith | 2017-08-05 | 2017-07-29
Service form | UI | Ruwan | 2 days | Done | Ruwan/Philip | 2017-08-06 | 2017-07-30
Invoice | Functional | Ruwan | 1 day | Done | Ruwan/Philip | 2017-08-07 | 2017-07-31
Issue method to get from database | Functional | Ruwan | 1 day | Done | Ruwan/Philip | 2017-09-03 | 2017-09-02
Add employees to service | Functional | Ruwan | 1 day | new | Ruwan | 2017-09-03 | 2017-09-02
Remove service status from UI | Modification | Ruwan | .5 h | Done | Ruwan | 2017-09-03 | 2017-09-02
Activate manager functions with authorized user name password | Functional | Ruwan | 1 day | new | Ruwan | 2017-09-05 | 2017-09-02
Show reorder level reach with red color | Functional | Ruwan | 1 day | new | Ruwan | 2017-09-05 | 2017-09-02